## Sheet1
Use Case | Use Case Name | Effort (Man*Weeks) | Iteration 2* (3/28/17) | Iteration 3* (5/1/17)
UC 1 | Login | 2 | 1 | 1
UC 2 | Logout | 2 | 1 | 1
UC 3 | Register | 2 | 1 | 1
UC4 | Reset Password | 2 | 1 | 1
UC5 | Create User Profile | 4 | 2 | 2
UC6 | Add Food (user) | 4 | 2 | 2
UC7 | Delete Food (User) | 2 | 1 | 1
UC8 | Add Water | 2 | 1 | 1
UC9 | Challenge | 4 | 2 | 2
UC10 | Search Food | 4 | 2 | 2
UC11 | Add Food (admin) | 2 | 1 | 1
UC12 | Delete Food (admin) | 3 | 2 | 1
UC13 | Add Exercise(admin) | 2 | 1 | 1
UC14 | Delete Existing Exercise (admin) | 2 | 1 | 1
UC15 | Add User | 2 | 1 | 1
UC16 | Delete User | 2 | 1 | 1
UC17 | Update Profile | 2 | 1 | 1
UC18 | Create Profile | 4 | 2 | 2
UC19 | Search ExerCise | 4 | 2 | 2
| Total Effort Estimated |  | 26 | 25
| Total Effort Available |  | 28 | 35
| Team Size | 7
Sum of the efforts of each row must not be less than the required effort | * Sum of the effort of each column must not exceed the ability of the team. Sum of the efforts of each row must not be less than the required effort.